## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things… |  | 10 | 5 | 5 | 0
create a couples room | Implement room class, player names | 1.5
create a couples room | Implement room page ui | 2.5
create a couples room | Wire "Start Game" button | 1.5
launch a game from my room | Implement board/game class (grid, moves, win, and draw logic) | 2.5
launch a game from my room | Implement game page ui (3x3 grid and back button) | 2.5
see real-time game state updates | Wire grid clicks: move, turn switch, win, and draw detection | 2
see real-time game state updates | Wire back button (game page to room page) | 1
all | Unit tests for room class | 1
all | Unit tests for board and game class | 1.5
| Estimate Totals | 16 | 10 | 5 | 5 | 0